## Data
Risk ID | Title | Status | Severity | Identified Date | Last Reviewed | Owner | Description | Likelihood (1-5) | Impact (1-5) | Inherent Score | Residual Score | Treatment Strategy | Treatment Status | Treatment Funding | Target Closure | Linked Findings | FAIR ALE Estimate ($K) | Notes
R1 | Supplier continuous-monitoring gap | Open | High | 2024-04-15 | 2025-12-11 | J. Park | Supplier risk program centered on annual reassessments only; no continuous monitoring of Tier-1 or Tier-2 vendors beyond AWS/Okta/Snowflake (which feed Vanta automatically). Reassessment cadence at 60% Q1 2026 against ≥90% target. The Change Healthcare ALPHV/BlackCat event (Feb-Mar 2024) is the primary illustrative case. | 4 | 4 | 16 | 12 | Mitigate — redesign program with continuous-monitoring expectations; expand Vanta feeds to Tier-2 vendors | In Progress | Funded FY26 | 2026-09-30 | GV.SC-04 GV.SC-05 GV.SC-07 GV.SC-09 | 420 | FY26 priority 7 in backgrounder; Audit & Risk Committee approved redesign Dec 2025
R2 | Recovery testing depth | Open | High | 2023-11-20 | 2025-12-11 | M. Tan | DR test program is annual and scope-limited to one critical service. Recovery tabletops historically conflated with IR tabletops. Service-tier RTO/RPO commitments (P1 4h/15m) not yet exercised against full-region failure scenario. | 3 | 5 | 15 | 12 | Mitigate — FY26 plan adds 2 recovery tabletops + 1 additional full failover; FY27 plan to introduce game-day-style exercises | In Progress | Funded FY26 | 2026-12-31 | RC.RP-01 RC.RP-04 RC.RP-05 RC.CO-03 | 580 | Board-acknowledged weakness; KPI tracking shows 1 full failover/year persisting through Q1 2026
R3 | Detection alert tuning debt | Open | Medium | 2024-09-05 | 2025-12-11 | M. Tan | Tier-1 SIEM alerts have approximately 28% false-positive rate. Detection use cases for legacy ETL cluster are incomplete. Alert response runbooks for Snowflake compute anomalies still draft. | 3 | 3 | 9 | 7 | Mitigate — Q1 2026 dedicated tuning sprint; expand DE.AE coverage with new use cases | In Progress | Partially funded | 2026-06-30 | DE.AE-02 DE.AE-03 DE.AE-06 DE.CM-09 | 140 | Tuning sprint approved; one engineer half-allocated for Q1 2026
R4 | PHI flow visibility into legacy ETL cluster | Open | Medium | 2023-06-12 | 2025-12-11 | A. Reyes | Legacy on-premises ETL cluster at Raleigh HQ supports a deprecating EHR integration for two long-tenured customers. Cluster is not in central asset inventory automation; data flow into Aurora is not fully instrumented; manual patching only. | 2 | 4 | 8 | 6 | Avoid — decommission cluster Q4 2026; compensating controls in place per CRA-LegacyETL-2025 | On Track | Funded FY26 | 2026-12-31 | ID.AM-03 PR.PS-01 PR.PS-05 PR.DS-02 | 210 | Customer migration to modern integration in flight; 60% complete as of Q4 2025
R5 | Third-party access reviews | Open | Medium | 2024-10-22 | 2025-12-11 | B. Olafsson | SaaS service-account access (non-human identities) is reviewed inconsistently; no automated discovery for OAuth-style access grants. Quarterly human access reviews are reliable (Q1 2026 KPI 98%) but service-account scope is gap. | 3 | 3 | 9 | 7 | Mitigate — Vanta access governance pilot Q2 2026; SCIM cleanup project in design | Planned | Funded FY26 H1 | 2026-09-30 | PR.AA-01 PR.AA-05 PR.AA-06 | 95 | Discovered during Q3 2025 SOC 2 fieldwork; auditor noted no exception but flagged in management response
R6 | Warm-DR readiness for Population Insights | Open | Low | 2025-04-08 | 2025-12-11 | A. Reyes | Snowflake-based Population Insights module has weaker DR posture than core Aurora-backed services. Data replication is asynchronous with 2-4h lag and warm-standby compute is not pre-provisioned in us-west-2. | 2 | 3 | 6 | 5 | Mitigate — FY27 plan to introduce hot-standby Snowflake account in us-west-2; documented in P2 service tier; current RTO 24h is achievable under existing posture | Planned | FY27 backlog | 2027-09-30 | RC.RP-04 RC.RP-05 | 65 | Population Insights is P2 (not P1) so current posture is within commitment; risk acceptance considered but rejected in favor of treatment in FY27
R7 | Insider-threat program maturity | Open | Low | 2025-07-10 | 2025-12-11 | J. Park | No formal insider-threat program. Background-check refresh on a 5-year cycle for engineers and security staff is in design. UEBA capabilities exist in Datadog but rules are not tuned for insider-threat use cases. | 2 | 3 | 6 | 5 | Mitigate — UEBA tuning Q3 2026; insider-threat policy POL-IT-01 in draft; baseline behavioral analytics on production access logs | Planned | FY26 H2 | 2026-12-31 | PR.AT-02 DE.CM-03 | 60 | GC and CPO partnership required; legal review of monitoring scope ongoing
R8 | Patient-portal CIAM hardening (Auth0) | Open | Low | 2025-03-14 | 2025-12-11 | B. Olafsson | Patient-facing portal CIAM is on Auth0 (separate from workforce Okta). Some legacy customers still permit username+password without MFA on patient-facing logins because customer healthcare populations include low-tech users. Risk-based step-up auth in design. | 2 | 3 | 6 | 4 | Mitigate — risk-based step-up authentication rollout Q3 2026; customer-tier MFA requirement contractual change for new contracts | In Progress | Funded FY26 | 2026-09-30 | PR.AA-01 PR.AA-03 | 45 | Patient breach impact lower than provider account compromise but still in scope
R9 | SBOM completeness for OSS dependencies | Closed | Low | 2024-02-01 | 2025-09-15 | A. Reyes | Software bill of materials (SBOM) generation for production services was incomplete; some Go services and the legacy ETL cluster were not covered. Closed Q3 2025 with full coverage via Snyk + GitHub Advanced Security. | 1 | 2 | 2 | 1 | Closed — full coverage achieved | Closed | N/A | 2025-09-15 | ID.AM-02 ID.AM-08 | N/A | Closed Q3 2025; verification by Coalfire HITRUST assessor confirmed
R10 | Workforce phishing susceptibility | Closed | Medium | 2024-03-15 | 2025-09-15 | P. Iyer | Quarterly phishing simulation click rate at 7.2% baseline (Q1 2024) against ≤3% target. Pebble Phish credential phishing succeeded in March 2024. | 4 | 3 | 12 | 4 | Mitigate — quarterly simulations + targeted retraining + FIDO2 mandate | Closed (target met) | N/A | 2025-09-15 | PR.AT-01 PR.AT-02 | N/A | Click rate at 2.4% Q4 2025; report rate 48%; closed as a register entry but program continues
COLUMN DEFINITIONS
Risk ID | Persistent identifier for the risk; never reused once assigned
Status | Open / Closed / Accepted / Transferred
Severity | Inherent severity rating: Low / Medium / High / Critical
Likelihood | 5-point scale per Risk Management Procedure PROC-RM-01: 1=Rare 2=Unlikely 3=Possible 4=Likely 5=Almost Certain
Impact | 5-point scale: 1=Negligible 2=Minor 3=Moderate 4=Major 5=Severe (PHI breach >500 records or comparable regulatory exposure)
Inherent Score | Likelihood × Impact before treatment
Residual Score | Likelihood × Impact after current treatment
FAIR ALE | Annualized Loss Expectancy from FAIR analysis (single-year basis); zero or N/A for closed risks
Linked Findings | CSF subcategories that map to this risk